## Sheet1
ITSC-3155 Software Engineering
Sprint Backlog
Story Tasks | Story Point | Assigned to | Estimated Effort | Day1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | Status | SPRINT REVIEW
As a staff, I want to create, read, update, and delete menu items so I can manage the menu | [9 empty] | Done
Create MenuItem model/schema |  | Devin
Implement CRUD endpoints for menu items |  | Devin
As a staff, I want to assign categories to menu items so I can classify and filter food easily | [9 empty] | Done
Add categories field to MenuItem model/schema |  | Devin
Implement endpoints to set and filter by category |  | Devin
As a staff, I want to edit prices, calories, and descriptions of items so I can input menu information | [9 empty] | Done
Add price, calories, and description fields |  | Devin
Update item details endpoint |  | Devin
As a customer, I want to filter menu items by category, price, or dietary tags so I can find what I want | [9 empty] | Done
Add filter options to menu API |  | Devin
Implement filter logic and response |  | Devin
As a staff, I want the system to auto-update and display menu item availability so customers see what’s in stock | [9 empty] | Done
Add availability/in-stock field to MenuItem |  | Devin
Hide unavailable items in menu responses |  | Devin
As a staff, I want to track ingredients and stock so I can maintain inventory levels | [9 empty] | Done
Create Ingredient model/schema |  | Devin
Inventory update endpoint |  | Devin
As a system, I want to auto-calculate menu item availability based on ingredient stock so only available items are shown | [9 empty] | Done
Link ingredients to menu items |  | Devin
Auto-calculate item availability from stock |  | Devin
As a staff, I want to link ingredients to menu items so I can define recipes and requirements | [9 empty] | Done
Implement recipe/ingredient linkage |  | Devin
Edit recipe requirements per item |  | Devin
As a customer, I want to remove and update items in my cart so I can manage my order | [9 empty] | Done
Add/remove/update cart item endpoints |  | Devin
Handle merge/update of existing cart items |  | Devin
As a customer, I want to select dine-in, takeout, or delivery when ordering so my order is handled correctly | [9 empty] | Done
Add order_type enum to orders |  | Devin
Handle order type during checkout |  | Devin
As a customer, I want to provide contact and address info so my order can be fulfilled | [9 empty] | Done
Add contact/address fields on order |  | Devin
Validate required customer info |  | Devin
As a customer, I want to view available menu items so I can decide what to order | [9 empty] | Done
Menu browsing endpoint |  | Devin
Return only available items |  | Devin
As a customer, I want to create and process orders so I can place my order online | [9 empty] | Done
Create Order model/schema |  | Devin
Order creation endpoint |  | Devin
As a customer, I want to receive a tracking number for my order so I can follow its progress | [9 empty] | Done
Generate tracking number on order |  | Devin
Include tracking number in confirmation |  | Devin
As a customer, I want to see order progress so I know when my order is ready | [9 empty] | Done
Expose order status to customer |  | Devin
Status lookup endpoint (by tracking/order id) |  | Devin
As a system, I want to check for valid order items and quantities so orders are accurate | [9 empty] | Done
Validate items and quantities at checkout |  | Devin
Reject invalid/unavailable items |  | Devin
As a staff, I want to update order statuses so orders move through the workflow | [9 empty] | Done
Staff endpoint to update order status |  | Devin
Persist and audit status changes |  | Devin
As a staff, I want to filter orders by status so I can manage kitchen workflow | [9 empty] | Done
Implement staff status filter for orders |  | Devin
Paginated results for filtered orders |  | Devin
As a staff, I want to view orders by date range so I can analyze order history | [9 empty] | Done
Add date range filter to orders |  | Devin
Return orders within range |  | Devin
As a staff, I want to add new menu items with basic details so the menu can expand | [9 empty] | Done
Endpoint to add new menu item |  | Devin
Validate required fields |  | Devin
As a staff, I want to manage ingredient stock levels so items are always up to date | [9 empty] | Done
Stock update endpoint |  | Devin
Decrement stock on checkout |  | Devin
As a staff, I want to view ingredient requirements for menu items so I can plan inventory | [9 empty] | Done
Endpoint to view ingredient requirements per item |  | Devin
Join items to required ingredients in response |  | Devin
As a staff, I want to create promotional codes so I can offer discounts | [9 empty] | Done
PromoCode model/schema |  | Devin
Create promo code endpoint |  | Devin
As a staff, I want to update and delete promotions so I can manage marketing | [9 empty] | Done
Update/delete promo endpoints |  | Devin
Validate promo dates/rules |  | Devin
As a customer, I want to submit reviews and ratings so I can share feedback | [9 empty] | Done
Submit review/rating endpoint |  | Devin
Validate rating range and required fields |  | Devin
As a customer, I want to view reviews for menu items so I can make better choices | [9 empty] | Done
Reviews display endpoint |  | Devin
Sort reviews by date |  | Devin
As a staff, I want to view and filter reviews so I can monitor customer feedback | [9 empty] | Done
Staff review filter/search |  | Devin
Hide PII in review responses |  | Devin
As a customer, I want to pay for my order using various methods so I can complete my purchase | [9 empty] | Done
Add payment method to order |  | Devin
Process payment at checkout |  | Devin
As a staff, I want to update stock so availability is accurate | [9 empty] | Done
Staff stock update endpoint |  | Devin
Validate non-negative stock updates |  | Devin
As a customer, I want to order without creating an account so I can check out as a guest | [9 empty] | Done
Guest checkout flag and minimal required fields |  | Devin
Skip account creation during checkout |  | Devin
As a customer, I want to add items to a shopping cart so I can manage my order | [9 empty] | Done
Add item to cart endpoint |  | Devin
Update/remove cart item endpoints |  | Devin
As a system, I want to save the order id in the browser so the cart persists | [9 empty] | Done
Store order_id in browser session/cookie |  | Devin
Restore cart by order_id on load |  | Devin
As a customer, I want to apply promo codes to my order so I can get discounts | [9 empty] | Done
Apply promo code and recalc total |  | Devin
Reject expired/invalid promo |  | Devin
As a restaurant owner, I want to view daily revenue so I can track performance | [9 empty] | Done
Revenue by date range endpoint |  | Devin
Return totals in cents (USD) |  | Devin
As a restaurant owner, I want to see average revenue per dish so I can assess performance | [9 empty] | Done
Compute revenue per dish (sum, count) |  | Devin
Filter by date range |  | Devin
As a restaurant owner, I want to see which dishes are most popular so I can plan the menu | [9 empty] | Done
Compute popularity by order count |  | Devin
Sort and return top N |  | Devin
As a restaurant owner, I want to view all reviews over time so I can spot trends | [9 empty] | Done
Reviews by date endpoint |  | Devin
Aggregate counts by rating |  | Devin
As a restaurant owner, I want to analyze menu item ratings so I can measure quality | [9 empty] | Done
Average rating per item endpoint |  | Devin
Return item_id, avg_rating, count |  | Devin
As a developer, I want to generate test data so I can demo features quickly | [9 empty] | Done
Test items, customers, orders, promos |  | Devin
Include edge cases (zero stock, expired promo) |  | Devin
As a developer, I want tools for automation so I can maintain quality | [9 empty] | Done
CI workflow to run tests on push |  | Devin
Pre-commit hook for lint/tests |  | Devin
As a staff, I want to print receipts for orders so I can hand them to customers | [9 empty] | Done
ESC/POS print endpoint (58mm) |  | Devin
Trigger print on paid order |  | Devin
As an admin, I want to configure restaurant info so receipts and UI are correct | [9 empty] | Done
Config endpoint (name, address, phone) |  | Devin
Load config at startup |  | Devin
As a system, I want to configure and apply tax so totals are correct | [9 empty] | Done
Apply NC tax rate to subtotal |  | Devin
Round to cents |  | Devin
As a system, I want to format receipts for the 58mm printer so they are readable | [9 empty] | Done
58mm layout and text wrapping |  | Devin
Cut/line-feed fallback |  | Devin
As a customer, I want to finalize my order with payment so I can complete checkout | [9 empty] | Done
Checkout endpoint sets paid and status |  | Devin
Handle promo/tax in final total |  | Devin
As a system, I want to handle errors throughout the flow so users see clear messages | [9 empty] | Done
Standard error response format |  | Devin
Log exceptions with context |  | Devin
TOTAL |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 14